## Application Details
Project Name | Santha Clinical Laboratory
Front End | Angular ver 11
Frontend Frameworks | ---
Third party API's | SMS, Payment Gateway
Backend | node js
Backend Frameworks | Springboot
Database | mongo DB
Application Archicture | MicroServices

## BackEnd Customer
S.No | User Story | Tasks | Expectation | Hours
1 |  | Application Initial Setup (Java) |  | 3
2 |  | DB Design (Mysql) |  | 5
login and registration
3 |  | login API (Gmail or Facebook) |  | 2 | POC Required
4 |  | login API (Username, password) |  | 2
5 |  | Register API 1. Regiser 2. OTP Validation |  | 4
6 |  | Reset password service(1. mail/number validate -> 2. Send OTP to mail/mobile -> 3. OTP validation -> 4. Password reset) |  | 8
Home/Work order
7 |  | List of services (Electrical, Plumbing, AC Repair) with slider Images. |  | 4
Booking page(Confrm order)
12 |  | Booking service |  | 4
My order page
13 |  | Order History API (Filter options All, Upcomming, Completed) |  | 3
14 |  | Get Single Order for Paymet page |  | 2
COD/Payment System
15 |  | Promo code validation |  | 2 |  |  | Not in scope
|  | Get Payment Info(Merchant acc Details) |  | 2
16 |  | Third party payment page API integration |  |  | POC Required
My profile page
17 |  | Get profile by ID |  | 2
18 |  | Update Profile Info |  | 2
19 |  | Upload profile Image |  | 4
20 |  | Remove Profile Image |  | 2
My offer page
21 |  | Get all offer list and slider images |  | 4
Common
22 |  | OTP Validation API (Sign up / login / Reset password) |  | 3
23 |  | Send OTP to user using M91 SDK. (Sign up / Resert Password ) |  |  | POC Required | MSG91
24 |  | Send Mail Notification to user (Order confirmation) |  | 5
25 |  | Send MessageNotification to user using M91 SDK (Signup Success, Order confirmation)
|  |  | Total Hours | 63
|  | Message | Regular Messege To Admin
|  | Call | Admin Number
|  | Notification | Not required

## BackEnd Vendor
S.No | User Story | Tasks | Expectation | Hours
1 |  | DB Design (Mysql) |  | 7
login and registration
2 |  | Register API 1. Register 2. OTP Validation |  | 4 | Login/Reset password api Not required here
3 |  | proof verification 1. Image upload 2. Document upload 3. send notification to Admin |  | 8
home page
4 |  | Slider Images . |  | 3
Leads page
5 |  | Get leads by professional ID |  | 3 | Is there any filter based on lat¦lng (Location based search)
6 |  | accept lead |  | 3
My Leads page |  |  |  |  | 8,9 can be a single service based on the need
7 |  | Get lead by accepted condtion |  | 2
8 |  | Start Job |  | 2
Quote page
9 |  | Get Quotetion for a service(Cunsulting Charge, GST, SGST info from DB) |  | 3
10 |  | Quote submit service |  | 5
Billing page
11 |  | Get Billing Info |  | 4
12 |  | Billing submit service(coustumer code validation) |  | 6 |  | Not in scope
Payout
13 |  | Get all case history by vendor id |  | 2
14 |  | Get case details by ID |  | 2
15 |  | Third party payment page API integration |  |  | POC Required
Others
16 |  | Sign Out services |  | 2
17 |  | Update Profile Info |  | 2
18 |  | Upload profile Image |  | 2
|  |  | Total Hours | 60

## BackEnd Admin
S.No | User Story | Tasks | Expectation | Hours
Admin App
1 |  | New Vendor list API |  | 3
2 |  | New Vendor Approval API |  | 2
3 |  | Vendor work completed details (Weekly completed job details) |  | 4
4 |  | Vendor Payment (Pyment Gateway integration) |  |  | POC Required
6 |  | Slider image for customer and vendor app |  | 6
7 |  | Offers CRUD |  | 6
8 |  | Customers Booking info API |  | 3 |  | Not in scope
9 |  | Pincode Schedule |  | 3 |  | Dashboard
10 |  | Booking Cancel |  | 3 |  | API Health check
11 |  | Booking info Mannual asign |  | 2
12 |  | Customer Booking info approval |  | 3
13 |  | Customer feedback update |  | 3 |  | This module may have more additional features
14 |  | Booking via Phone |  | 5
15 |  | Vendor¦customer booking Cancelation |  | 3
|  |  | Total | 46

## FrontEnd
S.No | User Story | Tasks | Expectation | Hours
1 |  | Application Initial Setup (Java)
2 |  | DB Design (MongoDB)
HOME
3 |  | Navigation Bar wih responsive
4 |  | about Us
5 |  | services given UI
6 |  | gallery
7 |  | Footer
About Us
8 |  | The page with routes and redirection
9 |  | About Us with the online booking facility
10 |  | UI-correction
Services Provided
11 |  | UI design of the servies
12 |  | Option for Booking the online appointment for every services
Services Provided
13 |  | Contact Us

## Billing
Initial Level Estimation Document *It may vary based on additional story.
Application | Estimated Hours | Billing Rate per Hour | Total Amount
BackEnd Customer | 63 | 750 | #NAME?
BackEnd Vendor | 60 | 750 | #NAME?
BackEnd Admin | 46 | 750 | #NAME?
|  | Total | #NAME?
Note*
POC Required Tasks are not Estimated.
Additional Task¦Story will be tracked seperatly.